## Yearly Plan 2021
Week | Project Setup | Continuous Integration | Continuous Delivery | Documentation
February | Create project plan
March | Setup infrastructure
April | Create scaffolding | Setup CI in GitHub | Setup CD in Azure
May |  |  | Deploy project | Create documentation
| Goals | Goals | Goals | Goals
| Create project plan | Setup CI | Setup CD | Create high quality documentation
| Setup project infrastructure |  | Deploy project
Difficulty
Easy
Medium
Hard

## Q2 2021
Week | Project Setup
2021-02-22 | Create project plan spreadsheet
2021-03-01 | Create Trello board
2021-03-08 | Create a GitHub repository
2021-03-15 | Create Azure account and subscription
2021-03-22 | Launch Azure Cloud Shell environment and create SSH key
2021-03-29 | Upload SSH keys to GitHub
Goals
Create project plan
Setup project infrastructure
Difficulty
Easy
Medium
Hard

## Q3 2021
Week | Project Setup | Continuous Integration | Continuous Delivery | Documentation
2021-04-05 | Create project scaffolding
2021-04-12 | Run local tests | Enable GitHub Actions in GitHub | Add Flask starter code to the project
2021-04-19 |  | Replace YAML code with scaffolding | Replace scaffolding code with Flask Machine Learning code
2021-04-26 |  | Verify remote tests pass in GitHub Actions UI | Authorize Azure App Service
2021-05-03 |  |  | Enable continuous deployment with Azure Pipelines
2021-05-10 |  |  | Add Azure Pipelines YAML based config file into GitHub
2021-05-17 |  |  | Enable GitHub and Azure Pipelines
2021-05-24 |  |  | Deploy the project in Azure Pipelines | Create README for the project
2021-05-31 |  |  | Make prediction | Create video demo for the project
Goals
| Create project plan | Setup CI | Setup CD | Create high quality documentation
| Setup project infrastructure |  | Deploy project
Difficulty
Easy
Medium
Hard
Note on B2: (Makefile, requirements.txt, Python virtual environment, test scripts)